## Open issues
No | Category | Issue | Details | To be done by | Priority | Raised | Due | Assigned to | Status | Closed on | Closing note | Visibility | Sub-project
| Electrical | Spare fan for shore converter to be delivered and fitted | Fan ordered from ATLAS on 10 Oct; ETA week 44 | Golden A/S | High | 2026-10-09 | 2026-10-30 | Iosif Bitzanakis | Open |  |  | External
| Electrical | Owner to confirm cable route on bridge | Waiting for captain | Owner / crew | Normal | 2026-10-10 | 2026-10-24 |  | In progress |  |  | External
| Mechanical | Yard to close the cable transit at frame 42 |  | Third party | Normal | 2026-10-05 |  |  | Closed | 2026-10-18 | Closed by the yard on 18 Oct | External

## Notes
Open issues import — how the columns are read
No: leave empty for new points. To update an existing point, use its number (OI-<project>-nnn) as shown on the tab or in the export — the number wins over the title.
Category: one of the issue categories of Settings › Issue categories (Mechanical, Electrical, Automation, Navigation & communication, Software / configuration, Documentation / class, Logistics / spare parts, Commercial / offer, Safety, Other, plus your own); abbreviations such as ELECTR or MECH are understood; empty = Other.
Issue: required. The title of the open point. A row whose Issue text already exists in the same sub-project updates that entry; new texts are created as manual entries.
Details: optional free text.
To be done by: Golden A/S (default), Owner / crew, Third party.
Priority: Low, Normal (default), High.
Raised: date the issue was raised (dd/mm/yyyy or yyyy-mm-dd); today when empty. Due: optional deadline.
Assigned to: full name of a Golden A/S portal account; unknown names leave the issue unassigned (listed as a warning).
Status: Open (default), In progress, Closed. Closed on and Closing note apply to closed rows.
Visibility: External (default, visible to the owner) or Internal.
Sub-project: only used when importing from the project page — the sub-project code (Y.01) or "code name"; on a sub-project page the column is ignored.
Run "Check only" first: nothing is written, you get the summary and the skipped rows.