## Projects
Project Code | Project Name | Customer | Vessel | Project Manager | Project Status | Sub-project Code | Sub-project Name | System | Sub-project Status | Order | Engineering % | Procurement % | Production % | FAT % | Installation % | SAT/HAT % | Commissioning % | Invoicing | Invoiced %
GY-85-02 | GY-85-02 Electrical & Automation | Golden Yachts | MY-GY-85-02 | Nikos Polykandriotis | Active | [12 empty] | partial | 40
GY-85-02.Y.01 | GY-85-02 Electrical & Automation | Golden Yachts | MY-GY-85-02 | Nikos Polykandriotis | Active | Y.01 | Main Switchboard | Power Distribution | Active | 1 | 100 | 80 | 40 | 0 | 0 | 0 | 0 | full | 100
GY-85-02.Y.02 | GY-85-02 Electrical & Automation | Golden Yachts | MY-GY-85-02 | Nikos Polykandriotis | Active | Y.02 | Lighting control | Lighting | Active | 2 | 90 | 60 | 20 | 0 | 0 | 0 | 0 | none | 0
GY-85-02.Y.03 | GY-85-02 Electrical & Automation | Golden Yachts | MY-GY-85-02 | Nikos Polykandriotis | Active | Y.03 | Bridge NAVCOM | Navigation & Communication | Active | 3 | 60 | 10 | 0 | 0 | 0 | 0 | 0

## Notes
Project-structure import — how the columns are read
One row per sub-project; repeat the main-project data on every row (the way the ERP exports it).
Project Code: the ERP code. Everything before “Y.” is the main project, the rest is the sub-project — GY-85-02.Y.01 → main project GY-85-02, sub-project Y.01.
A row whose code has no “Y.” part (e.g. GY-85-02) creates or updates the main project only.
Project Name, Customer, Vessel, Project Manager, Project Status: data of the main project. Customer is required the first time a project is seen; unknown vessels are created under that customer.
Sub-project Code: optional when the Project Code already carries the Y. part. Sub-project Name is required for a sub-project row.
System: the vessel system (Administration → Vessel systems). Unknown systems are added to the list automatically.
Sub-project Status: Active / On hold / Completed. Order: the position inside the project (1, 2, 3 …).
Engineering % … Commissioning %: the seven stage percentages, 0–100 (0.35 is also read as 35 %). An empty cell leaves the current value.
Rules:
• Main projects are matched by project code, sub-projects by project + code; existing ones are updated, new ones are created.
• Only filled-in cells overwrite existing values; an empty cell keeps what the portal already has.
• Nothing is ever deleted by an import. Tick “Check only” first to see the counts without writing.
Golden Automation Systems — Customer Portal · Import template R1
Invoicing : none / partial / full (blank keeps the stored value). Invoiced % : 0-100; with "partial" it is shown in the pill; 100 means full.